## Plan
Budget Bucket | Person-months | Person-months | est Q26.1 without 1.1, 1.2, 1.3 | estimate 1.1 | Estimation | MVP1.2-Q3 | Allocated in Q2 | estimate 1.3 | estimate 2.0 | Planned +used | est. left | plan left | Epic Description | 16.3. | 23.3. | 30.3. | 6.4. | 13.4. | 20.4. | 27.4. | 4.5. | 11.5. | 18.5. | 25.5. | 1.6. | 8.6. | 15.6. | 22.6. | 29.6. | 6.7. | 13.7. | 20.7. | 27.7. | 3.8. | 10.8. | 17.8. | 24.8. | 31.8. | 7.9. | 14.9.
[10 empty] | Q26.1 |  |  |  | 3.45 | 3.45 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45
[13 empty] | Engineer Capacity (Bruto) | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
[13 empty] | Engineer Absence |  | 0.4 | 1 | 0.4 | 0.4 | 0.6 | 0.6 | 0.2 | 0.2 | 0.2 |  | 1 |  |  | 1
[13 empty] | Holiday team members |  | nev 2d? | Nev = 5 | Easter | Easter | Nev = 3 | Arni = 1, Labour day | Arni = 1 | Ascension Day | Some public holiday |  | Nev = 5 |  |  | Arni = 5
| Line management | [11 empty] | Management Capacity (Bruto) | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45
| Line management absence | [11 empty] | Management Absence | 0.45
[13 empty] | Capacity incl. EM | 3 | 3.05 | 1.45 | 2.05 | 2.05 | 1.85 | 1.85 | 2.25 | 2.25 | 2.25 | 2.45 | 1.45 | 2.45 | 2.45 | 1.45 | 2.45
[13 empty] | Engineer Net capacity | 3 | 2.6 | 1 | 1.6 | 1.6 | 1.4 | 1.4 | 1.8 | 1.8 | 1.8 | 2 | 1 | 2 | 2 | 1 | 2
Overhead |  |  | 0.5 |  | 1 |  | 1 |  |  | 1.9 |  | 1 | Onoboard Omar/ Nam/ Reboot | [7 empty] | 0.5 | 0.5
Customer Support | Customer Support |  | 1.3 |  | 1.3 |  | 1.3 |  |  | 1.2 |  | 1.6 | bugs in production | 0 | 0.3 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
Customer Support | Operational Excellence |  | 4.6 |  | 7.6 |  | 7.6 |  |  | 7.8 |  | 7.7 | KTLO & OpEx (Nevena) | 0 | 0.1 | 0.5 | 0.5 | 0.5 | 0.6 | 0.6 | 0.5 | 0.5 | 0.5 | 0.7 | 0.4 | 0.6 | 0.5 | 0.5 | 0.7
Customer Support | KTLO | NAV-170423 | 1 |  | 4 |  | 4 |  |  | 0.8 |  | 4.2 | Data of Customer Fleets are ingested and visual in dashboard. (Nevena + intern?) | 0.1 | 0.1 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2 | 0.2
Critical Technical Debt | KTLO |  | 0 |  |  |  | 0 | 2? |  | 0 |  | 0 | Separate data and metrics for production cars from test data
Security & Compliance | KTLO | NAV-180094 | 2.5 |  | 3.2 |  | 3.2 |  |  | 2.5 |  | 4.3 | DATA storage and usage according to legal regulations. Database investigation and cleanup (Nevena / intern?) | 0.5 | 0.6 | 0.1 | 0.2 | 0.4 | 0.4 | 0.3 | 0.2 | 0.2 | 0.5 | 0.5 | 0.2 | 0.2
Customer Support | Customer Support |  | 3 |  | 2 |  | 2 |  |  | 0.1 |  | 2 | Onboard JLR to our metrics to ADP and Developer portal ( Arni ) | [6 empty] | 0.1 | 0.2 | 0.2 | 0.3 | 0.3 |  | 0.1 | 0.4 |  | 0.4
Customer Support | Customer Support |  |  |  | 1 |  | 1 |  |  |  |  | 1 | Q26.2 Support the DATA Flywheel loop | [9 empty] | 0.1 | 0.1 |  | 0.2 | 0.2 | 0.2 | 0.2
Customer Support | Other features | GOSDK-21982 | 1 |  | 1 |  | 1 |  |  | 1 |  | 1.2 | [NavSDK] Measure EV Quality Metrics Suite(Omar) | 0.1 | 0.1 | [10 empty] | 0.5 | 0.5
Critical Technical Debt | Solution design |  |  |  | 0.5 |  | 0.5 |  |  | 0 |  | 0.5 | SD Separate data and metrics for production cars from test data | [15 empty] | 0.5
Customer Support | Other features |  |  |  | 0.6 |  | 0.6 |  |  | 0.4 |  | 0.6 | MXNavi onboard AI powered EV Range via direct API's |  |  |  | 0.5 | 0.1
Self-Service ML EV Range - Phase 1 | Solution design | GOSDK-170623 | 1 |  |  |  | 0 |  |  | 0.6 |  |  | SD WL MVP 1.2: EV Metrics Dashboard Extension (Arni) | 0.3
Self-Service ML EV Range - Phase 1 | Solution design | GOSDK-170623 | 0 | 2 | 0.5 |  | 0 |  |  | 2.4 |  |  | SD WL MVP 1.2: Feature generation capability and process (Omar)
Self-Service ML EV Range - Phase 1 | Solution design | GOSDK-170623 | 0 | 2 | 0.5 |  | 0 |  |  | 1.9 |  |  | SD WL MVP1 .2: Define process to create prod-grade Fusion Model + create the first prod-grade version (Omar) | 0.5 | 0.5
Self-Service ML EV Range - Phase 1 | Solution design | GOSDK-170623 |  | 1 |  |  | 0 |  |  | 0.8 |  |  | SD MVP 1.2: WP 39: Add Consistency Check to Fusion Model Pipeline(Arni)
Self-Service ML EV Range - Phase 1 | Solution design | GOSDK-170623 | 0 |  |  |  | 0 | 1 |  | 0 |  |  | WL MVP 2: Add HRF based Metrics to dashboard
Self-Service ML EV Range - Phase 1 | Solution design | GOSDK-170623 |  |  |  |  | 0 |  |  | 0 |  |  | SD Beyond MVP2: SD Anomaly DATA Detection no 21
Self-Service ML EV Range - Phase 1 | Solution design | GOSDK-170623 |  |  |  |  | 0 |  |  | 0 |  |  | SD Beyond MVP2: Full scope ML+Fusion Model training/deployment pipelines
Self-Service ML EV Range - Phase 1 | White Label | GOSDK-19560 | 1 |  |  |  | 0 |  |  | 0.3 |  |  | WL MVP1: Extend analytics infrastructure no 11
Self-Service ML EV Range - Phase 1 | White Label | GOSDK-19560 | 2 |  |  |  | 0 |  |  | 0.7 |  |  | WL MVP1.1: E2E testing (rest of 1.0 test drives)
Self-Service ML EV Range - Phase 1 | White Label | GOSDK-170623 | 7 |  | 0.2 | 9.5 | 0.2 |  | 3 | 3.7 |  |  | WL MVP 1.1 + 1.2: EV Data Quality Monitoring Framework no 18 : Continuation from 2025 | 0.5 | 0.5 |  |  | 0.2
Self-Service ML EV Range - Phase 1 | White Label | GOSDK-170623 | 0 |  | 8 |  | 0 |  |  | 0 |  |  | WL MVP1.2: EV Metrics Data Model Extension
Self-Service ML EV Range - Phase 1 | White Label | GOSDK-170623 | 0 |  | 6 |  | 0 |  |  | 0 |  |  | WL MVP 1.2: EV Metrics Dashboard Extension
Self-Service ML EV Range - Phase 1 | White Label | GOSDK-170623 | 0 |  | 3 |  | 0 |  |  | 0 |  |  | WL MVP1.2: Ingestion of third-party data (Fisker & Dimo)
Quality improvements through ML/AI experimentation | White Label | GOSDK-170623 |  |  | 4 |  | 0 | [5 empty] | MVP 1.2: WP 39: Add Consistency Check to Fusion Model Pipeline
Quality improvements through ML/AI experimentation | White Label | GOSDK-170623 | 0 |  | 3.2 |  | 0 |  |  | 0 |  |  | WL MVP 1.2: Minimal scope of training/deployment pipelines
Self-Service ML EV Range - Phase 1 | White Label | GOSDK-170623 | 0 |  | 0 |  | 0 | 2.2 |  | 0 |  |  | WL MVP 1.2: Feature generation capability and process
Self-Service ML EV Range - Phase 1 | White Label | GOSDK-170623 | 0 |  | 6 |  | 0 |  |  | 0 |  |  | WL MVP1.2: Define process to create prod-grade Fusion Model + create the first prod-grade version
Self-Service ML EV Range - Phase 1 | White Label | GOSDK-170623 |  |  | 2 |  | 0 | [5 empty] | MVP E2E 1.2 Testing
Self-Service ML EV Range - Phase 1 | White Label | GOSDK-170623 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | WL MVP 1.2: Support Charm with the integration testing
Self-Service ML EV Range - Phase 1 | White Label | GOSDK-170623 | 0 |  |  |  | 0 | 1 |  | 0 |  |  | WL MVP2 Data collection - external fleets - AUI
Quality improvements through ML/AI experimentation | White Label | GOSDK-170623 | 0 |  |  |  | 0 | 2 |  | 0 |  |  | WL MVP2: In drive self-correction support
Self-Service ML EV Range - Phase 1 | White Label | GOSDK-170623 | 0 |  |  |  |  | 3 |  | 0 |  |  | WL MVP2: no 15 Extend analytics infrastructure semantically undefin attributes
Self-Service ML EV Range - Phase 1 | White Label | GOSDK-170623 | 0 | [5 empty] | ? | 0 |  |  | WL MVP2 : Add HRF based Metrics to dashboard
Self-Service ML EV Range - Phase 1 | White Label | GOSDK-170623 | [6 empty] | 3 | 0 |  |  | WL MVP2: E2E testing
Self-Service ML EV Range - Phase 1 | White Label | [8 empty] | 0 |  |  | BEYOND WL MVP2: Full scope of trainig/deployment pipelines
Self-Service ML EV Range - Phase 1 | White Label | [8 empty] | 0 |  |  | BEYOND WL MVP2: EV Data Collection for White-label EV routing [ nice to have AUI + NK1] - Jira (no jira ticket yet)
Self-Service ML EV Range - Phase 1 | White Label | [8 empty] | 0 |  |  | BEYOND WL MVP2: Make use of data collected in free-driving mode
0
0
0
| Sum of estimated work | Calculated | 24.9 | 5 | 22.4 |  |  | 9.2 | 6 | 26.1 |  |  | Should not have worked on this | 1 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0