## Plan
Epic Description | Estimation | Budget Bucket | Priority | Milestone | Link | Allocation Mode
Engineer Bruto Capacity | 4
Manager Bruto Capacity | 0.5
Engineers absence
Managers absence
NewHaven: Customer Support (NK2 context only) | 2 | Customer Support | 0 | Q2 | NAV-188674 | Uniform
NewHaven: Customer Support (not limited to NK2 context) | 4 | Customer Support | 0 | Q2 | NAV-188675 | Uniform
Customer Support: setting parameters and analyzing consumption prediction issues | 6 | Customer Support | 0 | Q2 | NAV-188672 | Sprint
Critical Tech Debt, security, compliance | 1 | Security & Compliance | 1 | Q2 |  | Gaps
Replace CalculateReachableDistance by CConsumptionAnnotationCalculator | 1.5 | Critical Product Debt | 1 | Q2 | NAV-197423 | Sprint
Patent (weather in consumption model) | 1 | Self-Service ML EV Range - Phase 1 | 3 | Q2 | NAV-171798 | Gaps
Trigger recalc for consumption curve change | 1 | Critical Product Debt | 2 | Q2 | GOSDK-197948 | Sprint
Battery Preconditioning in NavSDK | 0 | Critical Customer Commitments | 1 | Q2 | GOSDK-21210 | Sprint
White Label 1.3 solution design (except self-correction which is WP59) | 0.8 | Self-Service ML EV Range - Phase 1 | 3 | Q2 | GOSDK-170623 | Sprint
[1.2] WP #58 Research: Re-plannings (and other gaps) due to different model versions onboard vs online (physics vs fusion) [Support Jovan] | 0.5 | Quality improvements through ML/AI experimentation | 3 | Q2 | Online_vs_onboard_analysis.docx | Sprint