## Allocation
Budget Bucket | Epic / Capacity Metric | Priority | Estimation | Total Weeks | Mar.30 | Apr.06 | Apr.13 | Apr.20 | Apr.27 | May.04 | May.11 | May.18 | May.25 | Jun.01 | Jun.08 | Jun.15 | Jun.22
| Engineer Capacity (Bruto) |  |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
| Engineer Absence |  |  |  | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6
| Engineer Net Capacity |  |  |  | 3.4 | 3.4 | 3.4 | 3.4 | 3.4 | 3.4 | 3.4 | 3.4 | 3.4 | 3.4 | 3.4 | 3.4 | 3.4
| Management Capacity |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
| Management Absence |  |  |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| Management Net Capacity |  |  |  | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4
Customer Support | NewHaven: Customer Support (NK2 context only) | 0 | 2 | 2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0
Customer Support | NewHaven: Customer Support (not limited to NK2 context) | 0 | 4 | 3.9 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3
Customer Support | Customer Support: setting parameters and analyzing consumption prediction issues | 0 | 6 | 6 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
Security & Compliance | Critical Tech Debt, security, compliance | 1 | 1 | 1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0
Critical Product Debt | Replace CalculateReachableDistance by CConsumptionAnnotationCalculator | 1 | 1.5 | 1.3 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
Critical Customer Commitments | Battery Preconditioning in NavSDK | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Critical Product Debt | Trigger recalc for consumption curve change | 2 | 1 | 1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0
Self-Service ML EV Range - Phase 1 | Patent (weather in consumption model) | 3 | 1 | 1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0
Self-Service ML EV Range - Phase 1 | White Label 1.3 solution design (except self-correction which is WP59) | 3 | 0.8 | 0.8 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0
Quality improvements through ML/AI experimentation | [1.2] WP #58 Research: Re-plannings (and other gaps) due to different model versions onboard vs online (physics vs fusion) [Support Jovan] | 3 | 0.5 | 0.5 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | Weekly Allocation |  |  |  | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.5 | 1.5 | 1.5 | 1.4 | 1.4 | 0.9 | 0.9 | 0.4