## Plan
Budget Bucket | Person-months | Person-months | est Q26.1 without 1.1, 1.2, 1.3 | estimate 1.1 | Q2 | Estimation | Allocated in Q2 | estimate 1.3 | estimate 2.0 | Planned +used | est. left | plan left | Epic Description | Q26.1 | [13 empty] | Q26.2
[14 empty] | 2026-12-29 | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28
| Total capacity (calculated, incl. manager) | Calculated | [11 empty] | 6.45 | 6.45 | 6.45 | 6.45 | 6.45 | 6.45 | 6.45 | 6.45 | 6.45 | 6.45 | 6.45 | 6.45 | 6.45 | 6.45 | 6.45 | 6.45 | 6.45 | 6.45 | 6.45 | 6.45 | 6.45 | 6.45 | 6.45 | 6.45 | 6.45 | 6.45 | 6.45
[13 empty] | Engineer Capacity (Bruto) | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
[13 empty] | Engineer Absence | 2.6 | 0.6 | 1 | 0.4 | 1 | 1 | 1 |  | 0.4 | 1.4 |  |  | 1.4 | 2.6 | 2.2 | 2 | 1 | 1.2 | 0.4 | 1.2 | 0.6 | 1.8 | 0.6 | 0.2 | 1 | 0.6 | 0
[13 empty] | Holiday team members | Felix =5 Ralph = 3, Frieda = 1, Vlad = 1, Piotr =2, Dominik = 2 | Piotr = 2, Dominik = 1 | Frieda ill 5d? | Fireda ill 2d; | Frieda = 5 | Piotr = 5 | Dominik = 5 |  | Frieda 2 T | Ralph = 5 |  |  | Vlad = 5 | Vlad = 5 | Felix = 1 | Felix = 5 | Felix=1 | King's Day = 2 | Ralph = 2 | Frieda =1 | Piotr = 3 | Piotr = 5 | Piotr = 1 | Piotr = 1 | Frieda = 5 | Piotr = 3
[23 empty] | Vlad 2 illness |  |  | Felix = 2 | Frieda =4 | Easter = 6 | Vlad = 5 | Vlad = 4 | Labour Day = 4 |  | Ralph = 1 |  | White Monday = 4 | Poland Holiday =2
[27 empty] | Felix = 2 | Vlad = 4 |  |  |  |  | Ascension Day =4
Easter = 2
Line management | Line management | [11 empty] | Management Capacity (Bruto) | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45
Line management absence | Line management absence | [11 empty] | Management Absence | 0.1 |  | 0.2 | 0.45 | 0.45 | 0.45 | [5 empty] | 0.45
[13 empty] | Capacity incl. EM | 3.75 | 5.85 | 5.25 | 5.6 | 5 | 5 | 5.45 | 6.45 | 6.05 | 5.05 | 6.45 | 6 | 5.05 | 3.85 | 4.25 | 4.45 | 5.45 | 5.25 | 6.05 | 5.25 | 5.85 | 4.65 | 5.85 | 6.25 | 5.45 | 5.85 | 6.45
[13 empty] | Engineer Net capacity | 3.4 | 5.4 | 5 | 5.6 | 5 | 5 | 5 | 6 | 5.6 | 4.6 | 6 | 6 | 4.6 | 3.4 | 3.8 | 4 | 5 | 4.8 | 5.6 | 4.8 | 5.4 | 4.2 | 5.4 | 5.8 | 5 | 5.4 | 6
Customer Support | Overhead |  | 2.5 |  | 4 | 4.3 | 4 | 4 | 4 | 3.9 |  |  | Knowledge sharing, gaining expertise , learning on the job of new domains | 0.2 | 0.4 | 0.3 | 0.4 | 0.4 | 0.4 | 0.4 | 0.2 | 0 | 0.2 | 0.1 | 0.5 | 0.4 | 0.3 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.1 | 0.3 | 0.4 | 0.3 | 0.3 | 0.3
Customer Support | Customer Support |  | 2.6 |  | 2.6 | 2.8 | 2.6 | 2.6 | 2.6 | 2.6 |  |  | bugs in production reboot VS | 0.4 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.3 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
Customer Support | Customer Support |  | 2.6 |  | 3 | 3.3 | 3 | 3 | 3 | 3.2 |  |  | bugs in production reboot Other API'starting in Q4 | 0.4 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.6 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.3 | 0.3 | 0.2 | 0.1 | 0.2 | 0.3 | 0.2 | 0.3 | 0.3
Security & Compliance | Operational Excellence |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | API Security: 2nd batch - Geofencing API-Location History- Notifications
Maintenance & Release | Operational Excellence | NAV-176699 | 11.4 |  | 11 | 11 | 11 | 11 | 11 | 12.1 |  |  | Vehicle Service, CI/CD, Tracking AP, Routing API, NavSDK improvements | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.6 | 0.4 | 1.8 | 1.8 | 0.3 | 3.4 | 0.8 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 0.8 | 1 | 0.2
Security & Compliance | KTLO |  | 5 |  | 2 | 0.3 | 2 |  |  | 5.6 |  |  | Security: Vehicle Service TARA and PenTest and bucket for resolving issues | 0.5 | 0.5 |  |  | 0.5 | 0.5 | 0.8 | 0.8 | 0.2 | 0.1 | 0.2 | 1 | 0.5 | [8 empty] | 0.1 | 0.7 | 0.5 | 0.3 | 0.1 | 0.3
Customer Support | Other features |  |  |  | 0.4 |  | 0.4 |  |  | 0.8 |  |  | MXNavi onboard AI powered EV Range via direct API's | [9 empty] | 0.4 | 0.4 |  |  |  | 0.4
Security & Compliance | Security & Compliance | NAV-180094 |  |  | 2 |  | 2 | [5 empty] | [Discovery] Data deletion task | [23 empty] | 1 | 0.5 | 0.5
Customer Support | KTLO |  |  |  | 2 |  | 2 | [5 empty] | [Discovery] JLR onboard metrics (partial) NAV-186786 | [20 empty] | 1 | 1
Critical Product Debt | White Label | GOSDK-170623 |  |  | 19 | 2 | 19 |  |  | 2.6 |  |  | MVP 1.1 Overwrite Static vehicle parameters in NavSDK and Routing API | [9 empty] | 0.8 | 0.6 | 0.8 | 0.4 | 0.6 | 0.8 | 0.3 | 1 | 1 | 0.9 | 1.8 | 1.6 | 1 | 2 | 2 | 2 | 2 | 2
Critical Product Debt | White Label | GOSDK-170623 |  |  | 1.2 | 0.5 | 1.2 | [5 empty] | MVP1.1: E2E tests. (gap of vehicleModelId) | [25 empty] | 0.7 | 0.5
Critical Product Debt | White Label | GOSDK-170623 | 11.4 |  | 6 |  | 6 |  |  | 7.5 |  |  | MVP 1.1+1.2 Self service onboarding flow - automated | [6 empty] | 0.4 | 1.5 | 1 | 1.2 | 0.5 | 1.5 | 1.4 | 1.5 | 1 | 1 | 1.3 | 0.7 | 0.3 | 0.2
Critical Technical Debt | TechLT goals | TechLTRequest |  |  | 1 | 1 | 1 | [5 empty] | NavSDK Warning reduction (to be refined, request came in on 13.03) | [26 empty] | 1
Self-Service ML EV Range - Phase 1 | White Label |  |  |  | 1 |  | 1 | [5 empty] | [Discovery] NAV-188059: Repo refactor | [17 empty] | 0.4 | 0.6
Self-Service ML EV Range - Phase 1 | Solution design | GOSDK-170623 | 0 |  |  |  | 0 |  |  | 0.3 |  |  | SD Self service onboarding flow - automated (piotr+ralph) |  |  |  | 0.1 | [6 empty] | 0.2
Self-Service ML EV Range - Phase 1 | Solution design | GOSDK-170623 |  | 2 |  |  | 0 |  |  | 1.8 |  |  | SD white-label fusion model service (Ralph) | 0 | 0.3 | 0.1 |  | 0.2 | 0.2 | 0.2 | 0.4 |  | 0.2 | 0.2
Critical Product Debt | Solution design | GOSDK-170623 |  |  |  |  | 0 |  |  | 1.3 |  |  | SD Overwrite Static vehicle parameters in NavSDK and Routing API | [6 empty] | 0.7 |  | 0.6
Self-Service ML EV Range - Phase 1 | Solution design |  |  |  |  | 2 | 0 | [5 empty] | SD UXL suport for custom attributes
Self-Service ML EV Range - Phase 1 | White Label | GOSDK-170623 |  |  | 1.4 | 2.5 | 1.4 |  |  | 0 |  |  | MVP1.2: Support loading of historical weather data in HRF (WP?) | [23 empty] | 0.2 | 0.5 | 0.3 | 0.4
Self-Service ML EV Range - Phase 1 | White Label | GOSDK-170623 |  |  |  |  | 0 | [5 empty] | MVP 1.2 Testing
Self-Service ML EV Range - Phase 1 | Solution design | [5 empty] | 1 | [5 empty] | SD WP 9.2 Routing API extension calculateRoute
Self-Service ML EV Range - Phase 1 | Solution design | [5 empty] | 1 | [5 empty] | SD WP9.1 Routing API extension calculateReachableRange
Security & Compliance | Other features | GOSDK-169727 | 0 | [6 empty] | 0 |  |  | NAM database investigations
Self-Service ML EV Range - Phase 1 | White Label | GOSDK-169709 | 0.2 | [6 empty] | 0.2 |  |  | MVP1: E2E tests |  | 0.2
Self-Service ML EV Range - Phase 1 | White Label | GOSDK-19560 |  | 6 | [5 empty] | 6.6 |  |  | MVP1.1:VS Extension online. no 17.2 | 0.8 | 0.2 | 1 | 1.3 | 1.1 | 1 | 1 | 0.2
Self-Service ML EV Range - Phase 1 | White Label | GOSDK-170623 |  | 10 | [5 empty] | 7 |  |  | MVP1.1: Routing API extension calculateLongDistanceEVRoute (WP9) | 0.4 | 0.7 | 0.4 | 2 |  | 1.5 |  | 0 | 0 | 1 | 0 | 0.5 | 0.5
Critical Product Debt | White Label | GOSDK-170623 |  | 2 | [5 empty] | 2.2 |  |  | MVP1.1: E2E VariantID support for NavSDK | [5 empty] | 0.4 | 0.3 | 0.7 | 0.6 | 0.2 | alpha |  | beta
Critical Product Debt | White Label | GOSDK-170623 |  | 3 | [5 empty] | 2.5 |  |  | MVP1.1: AUI and VIL support of Vehicle Model ID - inner sourcing* (WP42.1) |  |  |  |  | 1 |  |  | 0 | 1 |  | 0 | 0.5
Self-Service ML EV Range - Phase 1 | White Label | GOSDK-170623 |  |  |  |  | 10 |  |  | 0 |  |  | MVP 1.3: Indrive self correction
Self-Service ML EV Range - Phase 1 | White Label | GOSDK-170623 |  |  |  |  | 2 |  |  | 0 |  |  | MVP1.3: Self-serve documentation and organisation
Self-Service ML EV Range - Phase 1 | [6 empty] | ? | [5 empty] | MVP 1.3 UXL suport for custom attributes
Self-Service ML EV Range - Phase 1 | White Label | GOSDK-170623 |  |  |  |  | 6 |  |  | 0 |  |  | MVP 1.3 WP 42.2 AUI and VIL/UXL support of Custom Consumption Model Attributes - inner sourcing
Self-Service ML EV Range - Phase 1 | White Label | GOSDK-170623 | [6 empty] | 1.4 | 0 |  |  | MVP2: Routing API extension calculateReachableRange(WP 9.1)
Self-Service ML EV Range - Phase 1 | White Label | GOSDK-170623 | [6 empty] | 1.6 | 0 |  |  | MVP2: Routing API extension calculateRoute (WP 9.2)
Self-Service ML EV Range - Phase 1 | White Label | GOSDK-19560 | [6 empty] | 15 | 0 |  |  | MVP2: white-label fusion model service
Self-Service ML EV Range - Phase 1 | White Label | GOSDK-170623 | [6 empty] | 1.5 | 0 |  |  | MVP2 : E2E tests
Critical Customer Commitments | Other features | GOSDK-167355 | 4 | [6 empty] | 5 |  |  | HELP KOOROSH/SIMON Amenities/Nearby POIs (Vlad+Felix) beta 31 jan | 0.3 | 1.3 | 1.4 | 1 | 1
Critical Customer Commitments | Other features | GOSDK-21500 | 2 | [6 empty] | 2 |  |  | HELP KOOROSH: Respect detailed opening hours : Health metrics (Piotr)beta 31 jan |  | 1 | 1
| Sum of estimated work | Calculated | 41.7 | 23 | 57 |  |  | 40.6 | 40.1 | 67.2 |  |  | Should not have worked on this | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Sum until that WP (incl.) |  | 41.7 | 65
| Capacity : | Engineer cap minus holiday | 67.2 | 67 | 69 |  |  | 68.6 | 68.6
Engineers minus holiday
| Capacity left for planning |  | 22.9 | 3 | 12 |  |  | 28 | 28.5