## Plan
budget Bucket | Type | Link | Priority | Estimation | Milestone |  | Allocation Mode | Some other column | Allocated | Epic Description | 29.12. | 5.1. | 12.1. | 19.1. | 26.1. | 2.2. | 9.2. | 16.2. | 23.2. | 2.3. | 9.3. | 16.3. | 23.3. | 30.3. | 6.4. | 13.4. | 20.4. | 27.4. | 4.5. | 11.5. | 18.5. | 25.5. | 1.6. | 8.6. | 15.6. | 22.6. | 29.6.
| Num Engineers (avg per week) |  |  | 2
| Engineer Capacity (Bruto) | [9 empty] | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
| Engineer Absence | [9 empty] | 0.6 | 1 | 1 | 1 | 0.2 | 1 | 1.2 | 0.7 | 0.2 | 0.2 | 0
| Engineer Net capacity | [9 empty] | 1.4 | 1 | 1 | 1 | 2.8 | 2 | 1.8 | 2.3 | 2.8 | 2.8 | 3 | 3
| Manager Capacity (avg per week) |  |  | 0.45
Line management | Management Capacity (Bruto) | [9 empty] | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45
Line management absence | Management Absence | [9 empty] | 0.1 |  | 0.2 | 0.45 | 0.45 | 0.45 | [5 empty] | 0.45
Overhead | Overhead |  | 0 | 1 | 1.2 |  | Uniform | 1.9 | 1 | Onoboard Omar/ Nam/ Reboot |  |  | 0 | 0 | 0.9 |  |  | 0.4 | 0.4 | 0.2 | [8 empty] | 0.5 | 0.5
Customer Support | Customer Support |  | 0 | 1.3 | 1.2 |  | Uniform | 1.2 | 1.6 | bugs in production | 0.1 | 0 | 0.1 |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.2 | 0.1 | 0 | 0 | 0.3 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
Customer Support | Operational Excellence |  | 0 | 7.6 | 1.2 |  | Uniform | 7.8 | 7.7 | KTLO & OpEx (Nevena) | 0.6 | 0 | 0.4 | 1 | 1 | 0.9 | 0.4 | 0 | 1.4 | 0.4 | 1.6 | 0 | 0.1 | 0.5 | 0.5 | 0.5 | 0.6 | 0.6 | 0.5 | 0.5 | 0.5 | 0.7 | 0.4 | 0.6 | 0.5 | 0.5 | 0.7
Customer Support | KTLO | NAV-170423 | 0 | 4 | 1.2 |  | Uniform | 0.8 | 4.2 | Data of Customer Fleets are ingested and visual in dashboard. (Nevena + intern?) | 0 | 0.2 | 0 | 0 | 0.2 | 0.2 | 0 |  |  | 0 | 0 | 0.1 | 0.1 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2 | 0.2
Critical Technical Debt | KTLO |  | 1 | 0 | 1.2 | 2? | Sprint | 0 | 0 | Separate data and metrics for production cars from test data
Security & Compliance | KTLO | NAV-180094 | 1 | 3.2 | 1.2 |  | Sprint | 2.5 | 4.3 | DATA storage and usage according to legal regulations. Database investigation and cleanup (Nevena / intern?) | [6 empty] | 0.2 | 0.4 | 0.2 | 0.5 | 0.1 | 0.5 | 0.6 | 0.1 | 0.2 | 0.4 | 0.4 | 0.3 | 0.2 | 0.2 | 0.5 | 0.5 | 0.2 | 0.2
Customer Support | Customer Support |  | 0 | 2 | 1.2 |  | Uniform | 0.1 | 2 | Onboard JLR to our metrics to ADP and Developer portal ( Arni ) | 0 | [6 empty] | 0.1 | [9 empty] | 0.1 | 0.2 | 0.2 | 0.3 | 0.3 |  | 0.1 | 0.4 |  | 0.4
Customer Support | Customer Support |  | 0 | 1 | 1.2 |  | Gaps |  | 1 | Q26.2 Support the DATA Flywheel loop | [20 empty] | 0.1 | 0.1 |  | 0.2 | 0.2 | 0.2 | 0.2
Customer Support | Other features | GOSDK-21982 | 0 | 1 | 1.2 |  | Sprint | 1 | 1.2 | [NavSDK] Measure EV Quality Metrics Suite(Omar) |  | 0 | 0.1 | 0 | 0.1 | 0.3 |  | 0.1 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | [10 empty] | 0.5 | 0.5
Critical Technical Debt | Solution design |  | 1 | 0.5 | 1.2 |  | Sprint | 0 | 0.5 | SD Separate data and metrics for production cars from test data | [26 empty] | 0.5
Customer Support | Other features |  | 0 | 0.6 | 1.2 |  | Sprint | 0.4 | 0.6 | MXNavi onboard AI powered EV Range via direct API's | [9 empty] | 0.2 | 0.2 |  |  |  | 0.5 | 0.1
Self-Service ML EV Range - Phase 1 | Solution design | GOSDK-170623 | 2 | 0 | 1.2 |  | Gaps | 0.6 |  | SD WL MVP 1.2: EV Metrics Dashboard Extension (Arni) |  | 0.3 | 0 |  | 0 |  |  | 0 | 0 |  | 0 | 0.3
Self-Service ML EV Range - Phase 1 | Solution design | GOSDK-170623 | 2 | 0.5 | 1.2 |  | Gaps | 2.4 |  | SD WL MVP 1.2: Feature generation capability and process (Omar) |  |  |  |  | 0.2 | 0.3 | 0.5 | 0.6 | 0.4 |  | 0.4
Self-Service ML EV Range - Phase 1 | Solution design | GOSDK-170623 | 2 | 0.5 | 1.2 |  | Gaps | 1.9 |  | SD WL MVP1 .2: Define process to create prod-grade Fusion Model + create the first prod-grade version (Omar) | [8 empty] | 0.2 | 0.6 | 0.1 | 0.5 | 0.5
Self-Service ML EV Range - Phase 1 | Solution design | GOSDK-170623 | 4 |  | 1.3 |  | Gaps | 0.8 |  | SD MVP 1.2: WP 39: Add Consistency Check to Fusion Model Pipeline(Arni) | [8 empty] | 0 | 0.5 | 0.3
Self-Service ML EV Range - Phase 1 | Solution design | GOSDK-170623 | 4 |  | 1.3 | 1 | Sprint | 0 |  | WL MVP 2: Add HRF based Metrics to dashboard
Self-Service ML EV Range - Phase 1 | Solution design | GOSDK-170623 | 4 |  | 1.3 |  | Sprint | 0 |  | SD Beyond MVP2: SD Anomaly DATA Detection no 21
Self-Service ML EV Range - Phase 1 | Solution design | GOSDK-170623 | 4 |  | 1.3 |  | Sprint | 0 |  | SD Beyond MVP2: Full scope ML+Fusion Model training/deployment pipelines
Self-Service ML EV Range - Phase 1 | White Label | GOSDK-19560 | 4 |  | 1.3 |  | Sprint | 0.3 |  | WL MVP1: Extend analytics infrastructure no 11 | 0.3
Self-Service ML EV Range - Phase 1 | White Label | GOSDK-19560 | 4 |  | 1.3 |  | Sprint | 0.7 |  | WL MVP1.1: E2E testing (rest of 1.0 test drives) |  | 0.5 | 0.2 | 0
Self-Service ML EV Range - Phase 1 | White Label | GOSDK-170623 | 2 | 9.5 | 1.3 |  | Sprint | 3.7 |  | WL MVP 1.1 + 1.2: EV Data Quality Monitoring Framework no 18 : Continuation from 2025 | 0.4 |  | 0.2 | 0 | 0.3 | 0.2 | 0.6 | 0.6 | 0 | 0.2 | 0.2 | 0.5 | 0.5 |  |  | 0.2
Self-Service ML EV Range - Phase 1 | White Label | GOSDK-170623 | 2 | 8 | 1.2 |  | Sprint | 0 |  | WL MVP1.2: EV Metrics Data Model Extension
Self-Service ML EV Range - Phase 1 | White Label | GOSDK-170623 | 2 | 6 | 1.2 |  | Sprint | 0 |  | WL MVP 1.2: EV Metrics Dashboard Extension
Self-Service ML EV Range - Phase 1 | White Label | GOSDK-170623 | 2 | 3 | 1.2 |  | Uniform | 0 |  | WL MVP1.2: Ingestion of third-party data (Fisker & Dimo)